Good Shepherd Catholic Church – Finance Minutes

January 14, 2026

6:00 PM

Present:  Tim Seprodi, Ken Schenk, Steve Piper, Ethan Broerman, Brian Lankford, Ron Pohl, Russell Gerteisen, Fr Zach, Brandon Ladley, & Dianne Thomas

Opening Praying – Fr. Zach

Adjustment to minutes regarding increase in preschool tuition requested by Ken Schenk. Minutes were then approved by Ken, with second motion by Steve Piper.

- Christmas Collection: Discussed how we could possibly increase. Most in favor of sending out a letter with Christmas Schedule along with a Christmas envelope as we have done in the past for many years.

- Expenses: Ken asking why we were in the negative: Due to the ordering of supplies. Should even out. Also asked about School Marketing. This was due to Sip & Support in September. It should zero out in December. Others are asking why the School Administration expenses were so high. This is due to our Full Time Youth First Social Worker. We are receiving a grant to pay for most of this; however, we are still waiting on the funds to hit our account. Youth First has told Mrs. Girten that the cost will go down considerably for next year. School account expenditures up also and believe it will even out, and just a timing issue.

- CMA:  We are at 71% of our goal with only 33% participation. Brian stated this is close to the same percentage as in the past. It didn’t seem to be affected by our capital campaign.

- Construction Update: All is going well. They are currently working on the tile in church, which will be followed by the carpet. Fr. Zach stated the Baptismal Font is on its way and should be here by Monday, January 19. Pews are expected to arrive by March 6. They were here to remeasure the pews Brian stated. It seems late at this stage, but they are still saying they should arrive on time.  Thunder Underground Wiring who is doing sound, and things for the hearing impaired said we were picking some humming, so CenterPoint had to fix power line to resolve this issue. We do need to test again to ensure the problem is resolved. We should be able to move back into church by the week of March 23, which is Spring Break. Therefore, our Mass is expected to be Palm Sunday Weekend.

It has been decided to go ahead and remodel the men’s & women’s bathrooms in church. All faucets have been changed out as they were old and some mismatched. Wallpaper is being taken off and replacing all water shut off valves. Going to fix the floors with an apoxy coating. Calling ICON for quote.

Garage is getting added on to and a new roof. It was decided to replace the rectory roof at the same time as it is over 20 years old. Price from Traylor was outrageously high so it was decided to get some estimates from other companies and have this done separately.

The new preschool addition should be finished by May 21. They are finished with the outside structure and are now working on the inside. The windows have been taken out of Maria Watson’s room which will be the new teacher’s lounge/lunchroom. We are asking Willscott to pick up the trailers the week of June 8. This would give us 2 weeks to move everything out of the trailers and into the new classrooms. Traylor would then have 2 months to finish the back parking lot before school starts.

We have paid Traylor just a little over $2,000,000 and have taken money out of our accounts at the Diocese to cover. In February we will probably be asking for a bridge loan to cover the rest. Brian is working on the details of that.

Some members expressed concern about what other big projects might come along as we are paying on the bridge loan. The following were mentioned by Brian:

- Resealing of parking lot this summer at a cost of around $26,000

- Brickwork all around the work needs to be fixed from the library all around to the gym. We just had the part outside of Amy Kessler’s classroom fixed at the cost of $13,000.  The company that built did not put a lintel beam at the top of the window.

- Roof on parish hall is 25 years old. Brian is keeping an eye on that.

- K-8 Tuition:  Brandon Ladley presented the 4 options for tuition for the 26-27 school year. Option one being no increase, option 2 $100 increase, option 3 $250 increase and option 4 $450 increase. Finance voted for option 3 of a $250 increase.

Meeting Adjourned